## Lead
Car Rental Application
Group Number - 2
Team Lead & Frontend Lead - Gangabathina Dhanush Kumar
Backend Lead - Jagruti Lalit Patil

## Status Track
Project Status Check :
Sl no. | Employee ID | Name | Domain | Module | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28
1 | 2583447 | Gangabathina Dhanush Kumar | Front-end | Controller | ER Diagram, Database, Division of Domain | Rental Entity | Service | Edit Cars and Types | Final Output | Preparation
2 | 2584101 | Dhorishetti Naveen Kumar | Front-end | Login | ER Diagram, Database, Division of Domain | Model, Repository | Repository | Controller | Final Output | Preparation
3 | 2584056 | Ellaboina Revathi | Back-end | Admin | ER Diagram, Database, Division of Domain | Rentals | Controller | Active Show | Final Output | Preparation
4 | 2583061 | Gayathirideve B | Testing | Show | ER Diagram, Database, Division of Domain | Clientside | Server Side | Databse | Testing the Code | Preparation
5 | 2583625 | Golle Sandhya | Front-end | Admin | ER Diagram, Database, Division of Domain | Add Admin details | Admin Controller | Server side | Final Output | Preparation
6 | 2582996 | Gowdacheruvu Kalpana | Back-end | User | ER Diagram, Database, Division of Domain | Model, Repository | User Controller | Car Booking | Final Output | Preparation
7 | 2584291 | Jagruti Lalit Patil | Back-end | Controller | ER Diagram, Database, Division of Domain | Model, Repository | Enums | Integration | Final Output | Preparation
8 | 2583302 | Janga Mahesh Reddy | Back-end | Payment | ER Diagram, Database, Division of Domain | Model, Repository | DTO | Service | Final Output | Preparation

## Status Meeting
Status Meeting Group - Car Rental Application
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2024-02-23 | 9:30 | ü | 2:30 | ü | 6:30 | ü
2024-02-24 | 9:30 | ü | 2:30 | ü | 6:30 | ü
2024-02-25 | 9:30 | ü | 2:30 | ü | 6:30 | ü
2024-02-26 | 9:30 | ü | 2:30 | ü | 6:30 | ü
2024-02-27 | 9:30 | ü | 2:30 | ü | 6:30 | ü
2024-02-28 | 9:30 | ü | 2:30 | ü | 6:30 | ü